Program of activities for The Holt School

Comenius Year 2 	October 2007 – June 2008

Comenius Coordinator – Natalia Jigounova

International Coordinator – Charlotte Wood

| Month | Activity | Detail | Dept/Faculty | Staff |
| --- | --- | --- | --- | --- |
| September | Create Comenius Team in school | Ji. Wo. Yvonne Smith, Nicky Coulson, Jessica Hope Palmer, Wesley Stear. Natalie Rogers, Di Jackson | Each faculty needs to nominate and send someone to meetings | HOF |
| October | Introduce PHARE to pupils Decide which class or groups to undertake activities with | A Year 8 French class (tbc) to collect information on holidays in the UK (sondage etc) Get classes (perhaps in L7 languages classes) to go onto PHARE https://phares.ac-rennes.fr/europe_in_4_schools/user | MFL / Natalie Rogers with set 1 year 8 | HOF |
| November | Movie Maker | Learn how to use it? | Drama IT? |  |
| December | Study the story of the Korrigans written in French but translated into English | One class from art to read the story and illustrate it Ji to give Ja a copy for her nominated class to read | Art | Ja |
| January 2008 | Study anthems and songs about the environment Write the next book of The Korrigans. The one where they meet other mythical creatures from UK and travel together. | Look at political/ protest/folk songs with one class in music and recording own version. Music dept to decide if feasible! Ji to speak to Sc by October half term 2007 to decide focus. English to nominate one class to read story and write a sequel to it involving typical mythical creatures | Music English | Sc/P Ruth Chambers |
| February 2008 February 2008 | Learning traditional dances Studying National Parks Research of the % of energy produced from different sources in each country and pollution resulting from each | Dance / PE. What is already in curriculum? Girls learn and perform a traditional English dance which we film/photo Geography visit to Lyndhurst is in a National Parks so could double up with coursework they do on that. Science to see if this fits in with SOW or use Yr 9 science club. End result would be compilation of data from Bulgaria, Italy and France to draw comparisons and findings | PE/Arts and Dance Humanities Geography Science | Sandra Moss Yvonne Smith Gemma Banks? Phillip Dunn |
| March 2008 | Studying and making summaries about 7 celebrities from UK Studying how the environment influences the way of life on a national level | MFL in French, German and Spanish can do this English as piece of creative writing? History – historical celebrities! Compare focus of history learning with other countries. Year 9 Geography – fits in with SOW. | MFL English History Sociology Geography | Wo Ruth Chambers Yvonne Smith |
| April 2008 | Study different sources of energy and pollution in each country Forum on Viv@ Vill@age about findings of pollution survey with Bulgaria, Italy and France | Need to set a date for the forum. Same group from science needs to feed back findings etc and take part in live ‘chat’ online. | Science | Phillipa Dunn |
| May 2008 | Studying typical diets in each partner country and health problems linked to them | Food Tech to conduct survey? Compile data , cook some French and Italian dishes – Yr 11 already cover this. Email for some Bulgarian recipes? | Tech Ji to email and ask .. | Jessica Sim |
| June | Exchange copies of The Korrigans and their Friends discover Europe | English to complete stories and send to partner schools | English | Ruth Chambers |
| July | Write evaluation of activities Collect all materials and evidence of projects and collaborative work | Ji/Wo to coordinate collecting together of evidence. |  |  |

Visits planned

Italy – 12 to 16th November

2 members of staff – Natalia Jiganova and one other – poss Jess or Wes or Natalie? And up to 10 pupils from any year! Need to get paperwork sorted and flights booked.