COMENIUS SCHOOL PARTNERSHIPS

PROGRESS REPORT

For 2-year multilateral and bilateral Partnerships

approved in 2007

Please send this progress report to your National Agency, duly completed and signed, by 30 June 2008, as requested in Article 7 (Monitoring, Evaluation and Control) of your Grant Agreement. The report will be used by your National Agency for monitoring purposes.

1. General information:

| Grant Agreement Reference No.: 07GBR01-COO600223-2 |  |
| --- | --- |
| Partnership title: Terr@ nostr@, vit@ nostr@ |  |
| Partner countries: Bulgaria, Italy, France |  |
| Partnership type: | ⁯ Multilateral (⁯ Renewal) |
| Your institution is: | ⁯ A partner |
| Name of your institution: The Holt School Address: Holt Lane, Wokingham, Berkshire RG41 1EE Telephone: +44 1189780165 Name of contact person: Dr N. Jigounova Telephone: +44 1189780165 (ext.243) E-mail: ji@holt.wokingham.sch.uk |  |

2. Partnership content

| 2.1. Please describe briefly the Partnership activities undertaken and the results achieved so far: |  |  |  |
| --- | --- | --- | --- |
| - Holt students wrote sequels to Corrigans story written by French students – ‘Corrigans in England’ and ‘Corrigans at the Holt’ and sent it to partner schools. - Y8 students designed questionnaire about holidays which were sent to French students and replies received. - We received posters created by French students on the topic of ‘What represents France?’ Out students draw posters on ‘What represents Britain’ which were sent to all partners school. Upon receiving national identity posters from Italy and Bulgaria we are planning to organise an exhibition at The Holt for students, parents and teachers. - Our music department working with students on recording instrumental background for ‘El condor pasa’ song which will be send to French school to record lyrics. - We received postcard from French pupils inviting our students to become pen-friends. Some students are now actively engaged in writing e-mails to each other. - Bulgarian students designed questionnaires on ‘Youth and identity in Europe’ which were sent to all partnership schools. Our students discussed and completed them in Psychology lessons and sent back for Bulgarian students and teachers to analyse. Results of this analysis will be sent to all four schools. - Students from all four partner schools have written and sent to each other questions for ‘Terr@ nostr@, vit@ nostr@’ Trivial Pursuit game to be played during Comenius visit to Ancona, Italy in November 2008. - Our students have written articles on National Festivals on PHARE (main web-platform for the project) that were commented on by students from France, Bulgaria and Italy - Technology department organised fortnightly ‘Comenius Cookery Club’ where Y8, Y9 and Y10 students try recipes sent to them by students from Italy, France and Bulgaria - From January 2008 we run well-attended Comenius Students Club. Each form has 2 Comenius representatives who attend Club meetings and give feedback to their forms. |  |  |  |
| 2.2. What problems/obstacles, have you met in the implementation of the Partnership, if any? How have these problems been solved? |  |  |  |
| - Lack of communication, e.g. Italian school is very slow in sending responses to messages/activities. Tried to solve problem by suggesting more to involve more teachers from Italian school into project to share responsibilities. - One person (French co-ordinator) is in control of the whole project which present problems is this person is absent or not well. - Main web-platform for the project (PHARE web-site) is set up in French. This was the choice of partnership co-ordinator, but presents problems as main language of the project is English and students from England, Bulgaria and Italy find it very difficult and demotivating. It was suggested by partner schools to convert PHARE in English (at least main menu). |  |  |  |
| 2.3. Mobility activities |  |  |  |
| Minimum number of mobilities planned (please tick as appropriate) | 12 |  |  |
| 2.4 Mobilities carried out between 1.10.07 and 30.6.08 (add rows if necessary) |  |  |  |
| Mobility description |  | Nr of participating staff | Nr of participating pupils |
| Comenius trip to Ancona, Italy |  | 2 | 6 |
| Comenius trip to Pleven, Bulgaria |  | 2 | 6 |
| Total number of mobilities |  | 4 | 12 |
| 2.5 Number of mobilities to be carried out by 31 July 09 |  | 12 |  |

3. Grantholder's declaration to be signed by the person legally authorised to sign on behalf of your institution and by the Partnership contact person in the school:

| "We, the undersigned, certify that the information contained in this Progress Report is correct to the best of our knowledge". |  |
| --- | --- |
| Date: 09/06/2008 Place: The Holt School Name and position of the contact person: Dr Natalia Jigounova Head of Social Sciences Comenius Co-ordinator Signature of the contact person: | Date: Place: Name and position of the Head of institution/organisation: Signature of the Head of institution/organisation: Stamp of the institution/organisation (if applicable) |

Including representatives of associated partners and - in the case of mobility involving persons with special needs - accompanying persons