Year 9 Technology Day 2008

notes re: organisation taken from meeting on 26 November 2007

Present:  Ca, Ar, Pt, Tm

Date of Technology Day:  Proposed to be held on 30th January 2008

Theme:  Carnival /celebration of ethnic diversity in Britain.

Cost:  Voluntary donation to be asked of students of £1 per person – Ca to look at whether the School Fund could be used to subsidise the event?

Organisation – 21 teams divided by House – each of the seven forms will be asked to provide names of five students to work in the Food Technology department during the day. These will work away from the main activity and will be responsible for catering – students to opt for this. The remaining students in each form will be divided into three groups. Each group will then contain approx. 30-5= 25/3 = 8 or 9 students max. per group.

These groups will be labeled numerically. There will be 21 groups in all.

| C | 1 Form tutors will be consulted about dividing groups up in a way that separates known trouble makers and which makes well balanced groups. |
| --- | --- |
| G | 2 |
| H | 3 |
| L | 4 |
| S | 5 |
| T | 6 |
| W | 7 |
| C etc. | 8 etc. |

School uniform need not be worn but trousers should be.

Positions within team:

- Accessories designers – x3.

- Model – x1.

- x 2 bin liner fashion designers.

- 2x notice board designers

- + 1 to add to the notice board team if there is an extra girl.

Job Descriptions

Accessories – 3 girls

To design and make head dresses or other ornamentation as decided by the groups in their team meetings. Team should decide strategy at team meeting.

T1 – groups 1-7  - PT

T3 - groups 8-14 - HD (

T4 – groups 15-21 - WI (needs to be asked to work P5)

BIN LINER FASHION – 2/3 girls

Design exotic carnival style costumes for the model, using available small bin liners.  Aim for a co-ordinated look.  Doesn’t have to be removable.  Sticky tape should be used – 1 small reel per group (marked per team to avoid reels getting lost or stolen)

CA/RB

CATERING – 5 girls

Make a selection of food for the others in their group (pretzels, Caribbean fruit baskets and samosas). Students will be awarded house points separate from the main competition.

AR/PA

MODEL – 1 girl

Based in the Hall in designated areas. Face painting demo to be arranged for makeup to look like an animal or oriental etc.

+ 1 staff in Hall

Notice Boards – 2 girls

There will be designated notice board spaces in the Technology corridor. These are to be used to develop a house Carnival notice board to reflect the activities of each house. In order to reduce the numbers in the corridor at any one time only 2 girls from each house will be allowed to put up displays.

T10/T7  TM/HE

STRUCTURE

  - Registration in Hall.  Tutors to register.

Briefing (Powerpoint presentation in the background on carnival themes. TM to produce)

Set the Scene

Introduce Day

Set out requirements

9.05   Go to pre-determined table arrangements in hall.

Teams to distribute and complete pre-printed group sheets for job allocation and pin up on notice board in Hall.

Teams to decide team strategies and design brainstorm. Decide on work to be done.

  - Individuals to designated work areas.

  - Practical – designing, then making.

  - Regroup in Hall for group discussion. Progress report back to other team members by one person per group.

  - – 11.20  BREAK

11.20 - 12.00pm  Making.

12.00 – 12.20 Regroup in Hall for group discussion. Progress report back to other team members by all. Catering team to bring food for groups to eat.

  - – 1.20 Practical work in areas. All costumes etc. and notice boards to be completed by 1.20

      - LUNCH BREAK

  - Registration in hall – Briefing then groups to get model and notice boards ready for judging. Food groups to go to clean food rooms.

  - Judging Areas – 	Food

Notice boards

Accessories

Outfit overall look

(Proposed Judges – Wendy Holland, Suzanne Richards, Ron Stewart, + new Governor?)

Judging takes place in Hall and Technology corridor – wait for judges)

Marks will be entered into a spreadsheet.

  - Back to Hall – all seated ready for presentation.

Group procession on stage – 30 sec introduction by a group member. Need for PA system to be set up.

3.25 Suzanne Richards to give a final conclusion.

      - Clear Tables etc.