British Council                                                                                                                                                       Connecting Classrooms

| PROJECT DETAILS |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project Plan for Othman Bin Affan School, U.A.Q. & Khadeeja School, Ajman |  |  |  |  |  |  |
| Project Title | My Health is in my food |  |  |  |  |  |
| Summary | The project seeks to develop genuine awareness of healthy diets and improve general education outcomes. |  |  |  |  |  |
| Activity Title Start and End Dates | Breakdown of Activity | Students & Teachers (age & no.) | Curriculum Subject | Resources | Outcomes |  |
|  |  | ME | ME | ME |  |  |
| Act. I: Food data collection: 1st Feb. '08 till 5th Feb. '08 | - Student Weekly Food Observation Form. - Student Food Questionnaire. - Family food Questionnaire. - Data analysis. | School 1: 37 Male Students Ages: (11-15) Teachers: 8 School 2: 30 Female Students Ages: (11-15) Teachers: 4 | - English Language - Science - Information Technology - Art | - Art material. - Dictionary. - School library. | Ss learn how to record and observe their diets. |  |
| Act. II: Field visits, Food data analysis & evaluation: 8th Feb. '08 till 12th Feb. '08 | - Field visits to schools. - Field visits to restaurants. - School canteen food & drinks analysis. | School 1: 37 Male Students Ages: (11-15) Teachers: 8 School 2: 30 Female Students Ages: (11-15) Teachers: 4 | - English Language - Science - Information Technology - Art | - Transport. - Telephone, fax & E-mails. - School curriculum. - Public libraries. - The World Wide Web. - Magazines& newspapers. - Dictionaries. | - Ss learn how to collect and record information about healthy food. - Ss learn how to compare and reproduce information about healthy food. - Ss get acquainted with other people’s lifestyles. - Ss accept others with tolerance. |  |
| Act. III: Food for health campaign. 15h Feb. '08 till 19th Feb. '08 | - Brochures - Posters - Lectures - Meetings - Reports - Local media | School 1: 37 Male Students Ages: (11-15) Teachers: 8 School 2: 30 Female Students Ages: (11-15) Teachers: 4 | - English Language - Science - Information Technology - Art | - Digital Camera. - Video camera. - CDs. - Printing materials. - Signs & boards. | - Ss develop their English Language skills. - Ss learn how to participate in a local campaign. |  |
| Act. IV: Information & material exchange: 15h Feb. '08 till 18th Feb. '08 | The partner schools exchange materials, information & experiences. | School 1: 37 Male Students Ages: (11-15) Teachers: 8 School 2: 30 Female Students Ages: (11-15) Teachers: 4 | - English Language - Science - Information Technology - Art | - Transport. - Telephone, fax & E-mails. - Boxes. - Mail. | - Ss get acquainted with other people’s lifestyles. - Ss compare their performance outcomes with others. |  |
| Act. V: Food arts & Crafts gallery: 15h Feb. '08 till 19th Feb. '08 | - Students are invited to participate in food art gallery. - Food Art contest. - Food art contest prizes. | School 1: 37 Male Students Ages: (11-15) Teachers: 8 School 2: 30 Female Students Ages: (11-15) Teachers: 4 All students can participate. | - English Language - Science - Information Technology - Art | - Display stands. - Drawing materials. - Writing materials. - Prizes. | - Ss learn how to express their ideas in drawing, painting and other different means. - Ss develop their artistic skills. |  |
| Act. VI: Open day: 22nd Feb. '08 till 22nd Feb. '08 | - Fun activities. - Healthy dishes. - Speeches & presentations. - School broadcast. | School 1: 37 Male Students Ages: (11-15) Teachers: 8 School 2: 30 Female Students Ages: (11-15) Teachers: 4 All students can participate. | - English Language - Science - Information Technology - Art | - Display stands. - Paintings. - Drawings. - Posters. - Game accessories. - Invitations. | - Ss learn how to utilize and connect their knowledge in different areas of the school subjects. - Ss learn to work cooperatively in teams. - Ss enjoy the learning environment. |  |
| Act. VII: School broadcast: 8h Feb. '08 till 26th Feb. '08 | Intensive School broadcast programme two days a week. | School 1: 37 Male Students Ages: (11-15) Teachers: 8 School 2: 30 Female Students Ages: (11-15) Teachers: 4 | - English Language - Science - Information Technology - Art | - Speeches. - Quizzes. - Health advices. | - Ss get encouraged to search for information. - Ss get encouraged to have healthy diets. - Ss are educated about other cultures. - Ss are educated about the dangers of unhealthy food. |  |
| Act. VIII: Fine food fair: 22nd Feb. '08 till 26th Feb. '08 | - Students display all their products. - Local traditional dishes. - International healthy dishes. - Fine art gallery. | School 1: 37 Male Students Ages: (11-15) Teachers: 8 School 2: 30 Female Students Ages: (11-15) Teachers: 4 All students can participate. | - English Language - Science - Information Technology - Art | - Display stands. - Paintings. - Drawings. - Posters. - Game accessories. - Invitations. - Certificates. - Digital Camera. - Video camera. | - Ss develop their social communication skills. - Ss learn how to evaluate and correct themselves. - Ss learn to adopt moderate lifestyles. |  |

| EVALUATION |  |
| --- | --- |
| Outcomes | What outcomes do you hope to achieve from this project? - Increase awareness of healthy diets. - Develop knowledge of social, health and food related issues. - Connect the different school subjects in joint activities. - Improve learning outcomes. - Refurbish learning environment. - Exchange learning methods, techniques and materials. - Improve students' English Language skills. - Develop team work and cooperation attitudes. - Work according to structured work plans. - Initiate self-learning and research methods among students. |
| Evaluation | How and when will you evaluate whether you have achieved the planned outcomes? - On-going evaluation, observation and assessment. - Pre-project questionnaire will be given to the Ss in the first week of February 2009. - Interviews – checklists – reports during the 3nd and the 4rd week of February 2009. - Final evaluation for the Ss products and activities: ( fair ) - Questionnaire for students, parents, guests and other teachers. - Documented visitors’ statements. - Post-project questionnaire will be given to the Ss in March 2009. - Comparing students’ learning outcomes before and after the project. |
| Other Details | Please include any additional relevant details in support of your project plan. Include details of any external partners or organisations that will also be involved in the project. - Additional school subjects are likely to be incorporated within the activities. - Activity dates are subject to slight modifications according to circumstances. - Contacts have been made to cover our activities by some local media institutions like: Al-Mua’lem Magazine, Al-Bayan Newspaper and others. - Our efforts will focus on our own school communities and will progress to cover other schools and hopefully larger circles. - We are trying to find local sponsors to sport our project financially. - Other school project activities are likely to be incorporated. |

| PARTNER SCHOOLS |  |  |
| --- | --- | --- |
|  | ME School 1 | ME School 2 (if applicable) |
| School Name | Othman Bin Affan School, U.A.Q. | Khadeeja School, Ajman |
| Country | UAE | UAE |
| Address | P. O. Box: 170, U.A.Q., UAE Tel.: 06/ 7664321 Fax: 06/ 7662009 | P. O. Box: 389, Ajman, UAE Tel.: 06/ 7433595 Fax: 06/ 7434454 |
| Main Contact Teacher | Suleiman Kasem | Rana Muhammad Yahia |
| Main Teacher’s Email | globalcitizen55@gmail.com | ranayahia00@hotmail.com |
| Main Teacher’s Phone | 050/ 5709776 | 050/ 6328691 |
| Assistant Contact Teacher (required) | Yousuf Afeef | Rana Sedqi |
| Assistant Teacher’s Email (required) | abujehad103@yahoo.com | rana.barghouthi@gmail.com |
| Assistant Teacher’s Phone (required) | 050/ 6780692 | 050/ 4829140 |

| AGREEMENT |  |  |
| --- | --- | --- |
| Each partner teacher should enter their name and the date to indicate that they have seen and agreed to the finalised version of this plan. |  |  |
|  | ME School 1 | ME School 2 |
| Name | Othman Bin Affan School, U.A.Q. | Khadeeja School, Ajman |
| Date | Thursday January 15th 2009 | Thursday January 15th 2009 |

| COMMUNICATION |  |  |
| --- | --- | --- |
|  | ME School 1 | ME School 2 |
| How often will you contact your partner schools? | Once a week at least. | Once a week at least. |
| What will be your usual means of contact? (e.g. email, phone…) | Telephone, Fax, Email. | Telephone, Fax, Email. |
| Which email address are you contactable on? (Assistant Teacher to be cc’d into emails) | globalcitizen55@gmail.com sskt99@yahoo.com | ranayahia00@hotmail.com |
| Which phone number(s) are you contactable on? | Tel.: 06/ 7664321 Fax: 06/ 7662009 Mob.: 050/ 5709776 Mob.: 050/ 6328691 | Tel.: 06/ 7433595 Fax: 06/ 7434454 Mob.: 050/ 6328691 Mob.: 050/ 4829140 |
| If your partner teacher is unable to get hold of you what should they do? | Drive to my school. Contact the project coordinator. Contact the Educational Zone. | Drive to my school. Contact the project coordinator. Contact the Educational Zone. |
| Signature | Othman Bin Affan School | Khadeeja School |