Action Plan (First Year)

| Start date | Core activity | Resources required | Core subject and theme | Who is responsible | Expected out come | By when |
| --- | --- | --- | --- | --- | --- | --- |
| 11/5/2008 | Sitting the general plan | Different ideas from the partnership schools | English | English Teachers | A clear plan of the project | 20/5/2008 |
| 21/9/2008 | Explaining the project to the teachers and the best students of the school | Power point workshop | All the best students and the teachers | Senior Teacher- Sultan Al Muqbali | Start doing the project following the plan | 22/9/2008 |
| 22/9/2008 | Exploring your country | Power point projects- posters – maps – flags - | English – Social studies - Arts - sports | Teachers of these subjects | Produce power point projects in the elanguages site- producing posters | 1/1/2009 |
| 15/11/2008 | Greeting cards and information about Eid / Christmas | Poster cards | English - Arts | Teachers of these subjects | Produce greeting cards and share them between the two schools by the post – make a film about what we do during the two occasions | 1/1/2009 |
| 1/1/2009 | A day in my life | Movie maker and video camera | English - home | English teachers and parents | Make a film about a day of an Omani student | 1/3/2009 |
| 1/3/2009 | Teaching Arabic/English | Video conference programme | English - Arabic | Teachers of these subjects | Teach Arabic to the British students and English to the Omani students | 1/5/2009 |